RESCUR Consortium Meeting 16th-18th September 2014
Viking Line, Stockholm, Sweden
Minutes of meeting

Participants Present 16th-18th September 14
Carmel Cefai and Paul Bartolo (Malta), Anastassios Matsopoulos and Mariza Gavogiannaki (Greece), Maria Assunta Zanetti and Valeria Cavioni (Italy), Renata Miljevic Ridicki (Croatia), Birgitta Kimber and Charli Erickson (Sweden), Celeste Simoes and Paula Lebre (Portugal), Ernesto Delfino (EU Commission).

Meeting between Project Coordinator and EU Commisson project coordinator
The meeting discussed the PR evaluation by the Agency and the letter sent by Mr Delfino to the project coordinator on 10th September 2014 and how the issues raised by the Agency and Mr Delfino in the letter were going to be addressed.

Presentation by Mr Eugenio Delfino
Mr Delfino described his role in the project to the consortium. He referred to the letter he had sent to the consortium and underlined that the PR evaluation is an opportunity for the partnership to do the necessary changes as recoemmended by the Agency to ensure these will be effected by the time the Final Report is presented at the termination of the project next year. He mentioned such issues as the overcharge of staff costs in the second lifetime of the project, quality assurance and dissemination and that these need to addressed by the consortium. In this respect, he argued, the PR evaluation is to be taken by the consortium as constructive feedback to improve the process of the proejct and its deliverbables and products in its second lifetime. He also said that the consortium has also the right to react to the RP evaluation and give its own feedback to the report; Mr Delfino would taking note of this feedback in his report to the Agency following the end of the 4th consortium meeting.

Presentations by each partner
Each partner introduced his university and described the partner’s involvement and contribution to the project according to each WP; these ppp will be uploaded on the partners’ platform (googledrive) and the project website this month (September 2014); all partners are to send a copy of their ppp to coordinator if they have not done so already

Consortium reaction to the RP evaluation

Objectives, results and products (5/10)
Deviation of WP2/3 and consequent postponement of handbook: this deviation made sense under the aspect of inclusive education, but it is not clear if all originally planned curriculum items are included in the existing drafts. Presented curriculum modules are suitable for teaching target group and are accompanied with handouts.
The consortium discussed at length this issue and sought to find a working formula to integrate the two different views which emerged in the discussion, namely a universal inclusive curriculum which mentions only the respective challenges and difficulties but does not mention in any way the groups of children experiencing such challenges, such as Roma children, refugee children, etc; and secondly, a resilience framework integrating both universal and targeted activities specifically for children at risk. As a result of the discussion it was agreed, that:
1. The framework agreed upon by all partners in July 2014 to address this issue (see box below) is a good solution to address the issue raised by the Agency. Each partner is to ensure its activities have been revised according to the 5 points as previously agreed (see box below; reference will be made to difficulties, risks, challenges but not to populations; a subtitle (target challenge) will be added to these activities.
2. In the introduction to the Manual, reference will be made to children at risk, including the 4 groups mentioned in our application; this will help to raise awareness amongst the teachers on the particular needs of such children. The following partners are to send one page (maximum) information on the needs of the following groups according to research by 18th October to coordinator:
  - Roma children (P4)
  - Refugee children (P1)
  - Disability (P1 and P6)
  - Gifted (P3)

Review of curriculum to justify removal of optional curriculum
At least 1 activity per subtheme for each age group (therefore 2 activities per theme for each age group, =2x3) would be focused on addressing difference, particularly issues related to  the difficulties which may be faced by the four groups mentioned in our application (stigma, labelling, prejudice, discrimination, exclusion, difficulty in accessing learning, school failure, lack of friends, bullying, culture clash/mismatch, language barriers)
- 1. In the story characters, including our two mascots,  we include a background  and a story which reflects the challenges/difficulties experienced by children at risk (roma, immigrants and refugees, disability, gifted children) (eg bullying, being left out, experiencing school failure)
- 2. We use questions about the story which underline the challenges (and solutions) presented in the story
- 3. In the activities following the story, we present the challenges these characters are likely to face and ask the children to work solutions to overcome these barriers and difficulties
- 4. Where possible, we ask children to choose their own challenges in the activities which are more related to their contexts and reality
- 5. We ask one or more question on what other children (children not at risk) can do to help the character in difficulty, so as to encourage a culture of understanding, solidarity and support towards children at risk.
- 6. We may make use of other resources, such as story books illustrating the values and issues we are discussing at that time, to complement and reinforce our own stories.

The postponement of the handbook is not fully reproducible: it might be beneficial to work on the handbook after terminating the curriculum work, but a structuring intermediate result should have been presented at this stage.
The consortium discussed at length this issue and the consequent overcharge of staff costs in the second lifetime of the project, particularly the translations of the manuals, and drew up a detailed action plan for the second lifetime of the project which will see the production and publication of high quality teachers handbooks and parents’ manual as planned in the original application. The agreed plan of action foresees the following actions between October 2014 and the end of October 2015:

CURRICULUM AND TEACHERS’ MANUALS
- October-December 2014: training of teachers and implementation of the pilot by the teachers
- December 2014/January 2015 : evaluation of the pilot
- Editing team reviews the present documents for coherence, quality of work, consistency, resources, by the end of December 2014; feedback will be given to the respective partners on modifications being suggested; partners will have one week to react. The revised version will be presented during the next consortium meeting in Pavai, March 2015
- Editing team consisting of Malta, Sweden and Portugal to meet in the third week of January 2015 in Portgual to finalise the curriculum draft
- January-February 2015: analysis of the pilot by each partner, writing brief report on findings and recommendations, report sent to coordinator by end of February/beginning of March 2015
- March 2015: 5th meeting in Pavia: review of curriculum on the basis of piloting reports
- April 2015: finalised curriculum sent to external experts
- May 2015: feedback from external experts
- June 2015: review of curriculum on the basis of experts’ feedback
- July 2015: final consortium meeting: discussion of final document, start of 3+1 manuals translation
- End of October 2015: all documents for publication translated: [fidelity issues to be discussed during the finalisation process in Pavia before we start translating); formatting by P3

PARENTS’ MANUAL
- October’14 – March’15: writing of the Introduction for the Manual by P4 and P1, discussed by whole consortium in 5th consortium meeting in March 2015 (Pavia)
- October’14-March’15: writing of each theme’s tools/strategies by each partner in collaboration with critical friend, discussed by whole group during the Pavia meeting
- March 2015+: external experts’ feedback, review, and translation as per Teachers’ Manuals schedule above.

Training of trainers was executed with the project’s key staff: it does not seem fully justified to execute this training in the context of the projects’ intentions and objectives. Need for key staff to receive this training was not sufficiently demonstrated
The partners who attended the training of trainers will be leading the training of teachers themselves together with supportive staff as required. Although the partners have expertise in various areas such as resilience, social and emotional learning, curriculum development and teacher education, few had specific training in training teachers on resilience/SEL programme implementation or in teacher resilience. The training was considered very beneficial by all partners and the training of teachers programme took many issues discussed during the training of trainers’ workshop.

Website has improved, but results restricted to partners. Information provided for visitors is poor.
It was agreed that more effort need to be invested to make the website more attractive and visible, particularly now that we are having material available for the public. Website is now available in all 7 languages of the consortium. It was considered rather premature to make the curriculum material produced so far available to the public since this has not been finalized and need to be edited by the internal QA team, piloted and reviewed by the external reviewers first. Various initiatives were planned however, to make more use of the website to promote the RESCUR project:
  - Partners and colleagues to LIKE the website
  - Summary of the project may be more detailed (P1 will do this in October 2014 and send to all partners for translation)
  - Uploading of a video clip in all languages on the project in October 2014 (P6)
  - Increase material for the public, including NEWS about consortium meetings and photos (eg 4th consortium meeting)
  - Mailing list of all those who visit the website
  - Regular uploading of abstracts, presentations by partners
  - Page for schools participating in the pilot to include also networking within the same partner country
  - Music, mascots, drawings also to be uploaded (resources section for the public)
  - Reorganize the platform(googledrive) and website partners’ area by each WP (P1 to do this by October 14)
  - Each partner to check that the uploaded version of the curriculum on the platform and website is the most recent one (September 14)

Coherence between workplan and activities carried out to date (5/10)

Almost all activities are modified, delayed or postponed, in some substantial cases with the consent of the agency. Not all modifications are adequately justified through the project management. It is to worry that towards the end of the project, partners might be overcharged: this issue could not be waived by the coordinator when providing supplementary information. It can be expected that the partnership will present useful results at the end of their activity period, but the outcome will be structured differently and the scheduling of activities has been entirely modified; it is recommended to rework the activity plan based on realistic assumption
Modifications and consequent delays were made following discussions and recommendations by partners during the consortium meetings. Though modifications did lead to consequent delays in some instances (eg. parents’ manual will be written following the teachers’ manual since the former is going to be built on the latter), changes were made following lengthy discussion between the partners, and when it was believed that these would in the end contribute to a better product based on the synergetic contributions of the partners. The comment that the coordinator could not waive the issue of overcharging in the supplementary material, reflects the collective style of management, where coordinator wrote that he wanted to discuss this with the other partners before making a decision on behalf of the whole consortium. The consortium acknowledged that in the second lifetime of the project there may be an overload of work, but feels confident that there is sufficient time to deliver the expected results on time and of the same high quality as described in the original application. A plan of action has been drawn, listing all the activities in the coming 13months, with clear deadlines for the completion and submission of work and products (see schedule of activities in the previous section of this document).

Management (5/5)
Partnerships agreements and management plans are not foreseen. Cooperation and planning is executed mainly during project meetings; these events are sufficiently prepared, agendas circulated in time and minutes are available; apart from meetings, communication is through skype and internal platform. Role of coordinator is not clearly defined: it seems that the partnership has a high impact on proceedings and decision making in the project implementation. Project manager should have had more influence on scheduling activities, partly also in knowing more details concerning the use of the allocated budget
Partnership agreements were signed between the coordinator and the other partners at the time of the submission of the application in January 2012 (sample attached with minutes). The coordinator’s style of management sought to reach a balance between an executive role, ensuring that products are delivered on time and as agreed, with a consultative role, giving the other partners an active role in decision making. It could be that too many changes were made to the original application on the basis of partners’ recommendations during the meetings; however, it was believed that this was compensated by having richer products based on the synergetic endeavor of the consortium. It was already foreseen by the coordinator, however, that the second lifetime of the project would see few changes and that it would be primarily dedicated to the implementation of actions and the development of final products. However, the coordinator will be taking a more directive role in ensuring that actions are implemented and products are produced on time by the whole consortium as agreed.

Partnership (7/10)
All partners are involved in project outcome, activities carried out show that the partnership is working successfully in terms of achieving the curriculum and the attached handouts. All partners are involved in all stages of the project implementation and all partners attended the group meetings. There is sufficient involvement of partners on internal platforms. The introduction of critical friend in activities seems to be a fruitful and efficient one. On the other hand, it seems that the many deviations from the original workplan are based on partner interventions, and not all of them are beneficial for the performance of the project. Not all partners supported the management sufficiently in administrative tasks.
The second lifetime of the project would see to the production of the deliverables as planned and the coordinator would take a more directive role in ensuring this takes place well and on time (see above).

Financial management (6/10)
On the whole expenditures made so far are in line with the budget and they are generally justified in regard to project activities carried out; staff costs, travel, subcontracting, and other costs are coherent with the actual implementation stage. But not all claims were adequately claimed in time. In view of the delay of many of the activities, the second half of project lifetime might see increased staff costs. 2 staff members from PT were on mobility in Zagreb, same travel dates, but one claimed 577 travel costs, other twice as much; explanation provided not helpful to clarify the situation. 107 researcher staff days are allocated for P6, 125 already were already claimed at midterm, staff days for technical staff is significantly below expectations for all partners (justifications made are vague). Picasso exhibition (Zagreb) and costs for lunch and dinners are questionable as partners have subsistence
The issue of overstaffing in the second lifetime of the project has been discussed and an action plan made to address this (see above sections). The issues raised by P6 have already been addressed, while the Picasso exhibition was considered to be a unique opportunity for the consortium to have a rich cultural experience during one of their meetings. The issue of costs for lunches and dinners paid by the hosting partner and not from subsistence allowance will be dealt by the coordinator’s financial office in collaboration with Mr Delfino.

Evaluation/quality assurance (3/10)
According to original application, activities foreseen in month 29; no activities were foreseen in the WP at an earlier stage; except informal talks with partners no activities were carried out and no written info could be provided (In view of modifications and deviations, it is recommended to review QA activities and start internal monitoring and product evaluation immediately; an external evaluator accompanying the activities would be beneficial
Given that the project main products were to be produced in the second lifetime of the project, it was considered appropriate by the whole consortium that QA takes place mostly during that period. Moreover the partnership did take a number of evaluation/QA initiatives prior to the submission of the PR earlier this year. These included amongst others, the use of critical friends which monitored and evaluated each other’s products, providing invaluable constructive feedback accordingly. A symposium on the project back in July 2013 was used to get external feedback on the project and this proved to be a very useful action in this respect. Moreover, a QA exercise was carried out during and after the 3rd consortium meeting in April 2014, when an ad hoc working group (P1 and P6) was established to streamline the learning objectives and structure of all the activities being produced by the six partners. The activities were consequently revised following the feedback of this working group. An internal review/QA team formed of P1, 5 and 6 has been set up during the present meeting (September 2014) to carry out an evaluation of the whole curriculum up to December 2014 on the basis of criteria established by the team; the team would also meet in January 2015 to conclude this phase of evaluation; further evaluation and review will be carried out by each partner, the QA team and the whole partnership following the pilot evaluation; further revision may take place as well following the review of the curriculum by two external experts.

Dissemination (5/10)
Point of weakness as activities are foreseen from month 25 and not many activities were planned, but some activities were carried out in this phase. Logo and disclaimer added; papers in scientific journals and in conferences presented; a flyer was drafted. Future masters in educational resilience recommended. Webpage is of limited value as no project results are made available to the public and language versions other than English not available. Would be beneficial to present real results under deliverable 7.3: at final report, partnership should provide proof of substantial products in this aspect. Partnership should intensify efforts to spread outcome
The consortium appreciates the need to take a more active active role in dissemination, but believes that it made sense that most dissemination activities were planned for the second part of the project when products and results are already available and could be shared with the public. In the meantime it has presented an international conference symposium on the project with the participation of all members in July 2013, four presentations in international conferences and seminars by the coordinator or members of the consortium, as well as a peer reviewed paper in English in a scientific journal; another paper in another British journal is due to be published in June 2015 (abstract already accepted). Flyers in all languages have been disseminated in various countries and during conferences while a feature on the project has been published int he coordinator’s university website, electronic noticeboard and an international newsletter. Various steps have already been taking place on the holding of a Eueopean masters in resilience and wellbeing in schools, but an action plan has now been drawn up on this deliverable (see dissemination below). Other initiatives include an edited book with another EU LLP project, symposia in international conferences, and the estbalishment of Special Interest Group on resilience in education (see below). Various dissemintion iniatives will be taking place also during the next ENSEC conference in 2015 (Lisbon) hosted by one of the partners (see below). The wesbite will continue to be improved and material for the public increased (see previous and below actions).

Piloting
Training of teachers
- Each partner gave a presentation of their piloting in schools, with most partners having already translated their theme or are in the process of doing so, and having already identified and selected the schools and teachers taking part in the pilot.
- Training of teachers have started or will be carried out by all partners in September or October 2014. It will take place over 3 days with about 15 hours of training in total and will be led by a trained trainer.
- A number of partners have more than 20 participants, but it was decided to include the extra teachers, also for dissemination purposes, while ensuring that the total number of participants would not exceed a number which may interfere with the nature of the skills-based, interactive workshop
- Each of the 20 participants will be provided with a training pack in the language of the partner
- The workshop will include the following elements, but it is up to the individual partner to structure the training according to its particular needs:
    - Objectives of the training
    - Introducing RESCUR and the partners
    - The role of the schools and teachers in the piloting project
    - Defining resilience and the need for a resilience curriculum in school
    - Introducing the theme and subthemes to be implemented, including the rationale, principles, and framework
    - Activities: various activities from the two subthemes within the manual will be adapted for teachers and then role played in the group (eg one activity from each set of activities), and then processed (how relevant is this activity to the students in your classroom, what challenges might there be in implementing it successfully, etc);
    - The training focus is experiential, making use of the SAFE approach
    - Issues of implementation (implementation index supplied with the pack) discussed in groups
    - Assessment checklist completed and discussed (included in the pack)
    - Teachers’ own resilience: the four dimensions of being a resilient teacher, ways to build teachers’ resilience
    - Coaching and mentoring during the implementation
    - Evaluation of the pilot at the end
    - Evaluation of training (1 hour at the end) to include checklist on what have we learnt, recommended modifications to the programme (see Appendix 1 below)
    - Programme theme will be revised according to the feedback by the teachers and the trainer in collaboration with the rest of the consortium members.

Implementation
- the implementation of pilot will take place during the first term of the 2014-2015 scholastic year and concluded by the end of December 2014
- it consists of 6 weeks programme with one 45 minutes session every week (or two 20” sessions particularly with the early years)
- teachers will focus on activities in line with the developmental level of their students (eg. avoid using advanced lessons when the year group is still at the basic level- the three year age band within each age group may be used as an indicator of the age of the children eg Early Primary : 6, 7, 8 years: a class of six year olds may thus focus more on the Basic activities within each set)
- during the implementation, teachers will receive coaching and mentoring by the trainer

Evaluation
- evaluation of the piloting will be made by the researcher from each respective partner country within 1 month from end of the piloting (Dec 14-Feb 15)
- Evaluation will consist of the following tools
    - A classroom behaviour and relationships checklist on the whole group completed by the classroom teacher (not on individual children) at the end of the pilot
    - Qualitative data on programme process and outcomes based on interviews, focus groups and questionnaires with teachers and students, at the end of the pilot
    - Reflexive journal of observations kept by the teachers (optional, but strongly recommended) at the end of each lesson.
- Data analysis and report writing by each partner will take place in Jan-March 2015; the report in English will be submitted to the coordinator by 15th March 2015 by each partner. These will be discussed in the fifth consortium meeting in Italy in March 2015.
- Tools
    - A classroom behaviour and relationships checklist on the whole group completed by the classroom teacher (not on individual children) at the end of the pilot, focusing on the topics of the 2 subthemes of each theme covered during the implementation at the three age levels (see appendix 2A)
    - A questionnaire/focus group/interview schedule completed by teachers on the curriculum and implementation process (see appendix 2B), completed by at least about one third of the teachers (around 7 teachers)
    - A focus group with about 3 groups of children, one for each age group (early years, early primary, alter primary), of about 6-8 students each, exploring the children’s views of their experiences of the curriculum (see appendix 2C). Students will be also asked to give their feedback on the mascots
    - A Reflexive journal of observations kept by the teachers (optional, but strongly recommended): about half to one page at the end of each lesson with their reflections on the activity of the day (see appendix 2D).

Staff days allocated for piloting (not including the translation)
- 4 days for each partner to organise the training of teachers in own respective country
- 4 days for each partner to organise the pilot implementation in own respective country
- 4 days for each partner to coordinate the evaluation
- 4 days for each partner for overall collaboration
- 20 days for each partner for data collection, inputting and analysis
- 15 days to each partner to train 20 teachers in own country

RESCUR Mascots
It was agreed that:
- The mascots will feature in all manual resources/handouts for students since these are the trademark of the project, but that they will feature at the bottom so as not to be too distracting for the children
- In the focus groups the children will be asked about the mascots and make their own drawings, which will be sent to Antonia for the final version of the mascots

Copyright issues
 The copyright issues were discussed and agreed during the 3rd meeting in Crete (May 2014, see minutes on googledrive/website), but an issue arose about who owns the copyright of the translated editions, namely whether the respective partner or the whole partnership. The coordinator said that he has no objection that the respective partners will have ownership on their translated version, but will need check first with the Consortium Agreement signed by each partner with the University of Malta and with the administration of the University of Malta; feedback on this will be sent to partners in October 2014.

Assessment checklists for the early years
The partnership agreed that textual self assessment checklists for the early years were not appropriate for very young children and that we need to consider alternative forms of assessment for such age groups (4-5 year olds). A discussion followed on appropriate methods of self assessment for young children in view of their limited literacy and cognitive ability; action oriented methods, making use of play, role play and story telling may be considered. P2 and P1, as leaders of this WP, are to do further research on this and draw up a short memo for the consideration of the whole partnership by the end of October 2014

Quality assurance/streamlining

Streamlining of activities
- Each partner is to see that the activities follow the same format as agreed in the second and third consortium meetings including resources and handouts
- Each partner is to ensure the changes suggested by P1 and P6 following the learning goals review earlier this year, are carried out in their respective theme
- Each partner is to ensure that the uploaded version of their activities on the website, is the revised one
- Those partners with no or limited handouts will be working on having a number of such handouts, ideally one for each set of activities (B/I/A) where appropriate.
- Material needs to be inspiring, attractive, user friendly, relevant

Internal review/QA team
- An internal review/QA team formed of P1, P5 and P6, has been set up to carry out an evaluation of whole curriculum up to December 2014 on the basis of criteria established by the team; the feedback of the team will be sent to each respective partner who will have one week in which to respond back to the team (P3 will see the formatting and style).
- The team will meet in Portugal between 23-25th January 2015 to finalise the curriculum
- In the March 2015 meeting in Pavia, the team together with the other partners will review the feedback from the piloting in the 6 countries and make recommendations for the revision of the curriculum accordingly
- In April 2015 the team will send the manuals, including Parents’ Manual, to two external experts
- In June 2015, the team, in collaboration with the other partners will recommend any changes to the curriculum according to the external experts’ reports
- In the July 2015 sixth meeting, the partnership will finalise the final version of the teachers’ and parents’ manuals so that the translations can start immediately after that.
- P3 will see to a common formatting and style for the teachers’ and parents’ manuals

External experts
- The general criteria for the external experts are that one will be an expert on educational resilience (and related social justice and equity) and the other on curriculum design, implementation evaluation, and that they will be European. Other criteria include
  - Have teaching skills and teacher education background
  - A child perspective
  - Knowledge of developmental psychology, health promotion, and resilience
  - Practitioner, and also a sound background in research
  - Do not come from the six partners in the consortium (but may come from the same country)
  - Do not have any conflict of interest with any member of the consortium, such as being colleagues with any member of the consortium; all members of the consortium are to declare any conflict of interest with any nominated candidate.

- List of potential experts
  - Anne Marie Sorlie: Norway (curriculum)
  - Luca Sciarroni: SUSPA (curriculum
  - Neil Humprhey Manchester University (programming SEL)
  - Katherine Weare (SEL, curriculum)
  - Others…
- Partners are to send their nominations of other possible experts to Birgitta and Carmel by mid October 2014

Parents’ Manual

- There will be one manual for parents for the 3 age groups and will include the following sections:
  - Rationale of the activities, explaining resilience and its importance in young children’s development, and the role of parents in fostering resilience in their children. This will be written by P4 and P1
  - 6 Themes, with one chapter on each theme and subthemes written by each respective partner as follows:
      - Rationale for the theme and subthemes (developed from the teachers’ manual)
      - Tools for parents on each subtheme within each theme (how parents may help their children develop…); these will seek to empower the parents’ role in resilience building and avoid the trappings of patronizing advice on what parents should do
      - Strategies would be general but with specific examples; would be culture-friendly reflecting different cultures; and would be developmental with examples from early years (eg 5 years old) and late childhood (eg 11 years)
      - Resources for parents (further readings, guides, internet links,…)

* A model template for the respective theme tools/strategies will be sent to all partners by P4 and P1 by 15th November 14

* 15th December 14: each partner to send completed tools template to critical friend

* 15th January 2015: each partner to send completed template to P4 and P1 (Renata, Mirjana, Carmel)

* 15th March 2015: Editing team (P4/P1) will present the revised version to whole partnership for discussion during the Pavia meeting

Dissemination:
- Each partner’s dissemination initiatives were presented to the whole group; these will be uploaded on the platform and the website by P1 in September 2014
- P6 provided an excel sheet with the list of dissemintation activities between September 14 and October 15; each partner is to send any new dissemination initiative (both international and local -see ppp by P6 enclosed) including conference presentations, publications, features, to Paola and Celeste, who will include these on the dissemination template deveoped by P6 on the website
- A new paper on RESCUR is being written by the whole consortium in the International Journal of Multicultural Education, a peer reviewed scientific journal, in 2015; the abstract has already been accepted. P1 and P3 are leading the paper together with P 6 and P2, but the paper will include all partners as co-authors. The first draft of the paper will be presented in January 2015; further details on this later on this year.
- ENSEC symposium: a RESCUR symposium by the whole partnership will be presented during the ENSEC conference in July 2015 in Lisbon; the abstract will be submitted by January 2015; further details on this later on this year
- P1 is establishing an ENSEC Special Interest Group in Resilience in Education, with a call for members being issued in the ENSEC newsletter in September 2014; all members of RESCUR have showed interest in joining and contributing to the SIG (see appendix 3)
- RESCUR partners have been invited to write a chapter on educational resilience in their own country in an edited book based on three projects, namely RESCUR, ENTRÉE (a teacher resilience EU LLP project) and Keep Cool (an Australian programme on teacher resilience). The book will be published in 2016 once both RESCUR and ENTRÉE have been concluded. Further details will be provided by coordinator, whos is liaising with the other projects’ coordinators, later on.
- P6 to provide 25 RESCUR posters to each partner, additional flyers in English to those who want, and RESCUR Manual brochures later on in 2015 which will be distributed also during the half day training in each country
- ENSEC 2015 Conference in Lisbon
    - Symposium by RESCUR team
    - Banner/roll-on on RESCUR
    - USB stick on RESCUR in the conference delegates pack
- Half day seminar in each partner country (Nov 2015) to include key stakeholders and policy makers in the country/region, need to organized before the end of November 2015 but possibly after the manuals have been published
- As exploitation, partners may also organize a one week resilience course for teachers and teacher educators through ERASMUS programme in 2016+
- Website
    - Partners and colleagues to LIKE the website
    - Summary of the project may be more detailed (P1 will do this in October 2014 and send to all partners for translation)
    - Uploading of a video clip in all languages on the project in October 2014 (P6)
    - Increase material for the public, including NEWS about consortium meetings and photos (eg 4th meeting)
    - Mailing list of all those who visit the website
    - Conference abstracts, presentations
    - Page for schools in the pilot to include also networking within the same partner country
    - Music, mascots, drawings also to be uploaded (resources section for the public)
    - Reorganize the platform(googledrive) and website partners’ area by each WP (P1to do this by October)
    - Each partner to check that the uploaded version of the curriculum on the platform and website is the most recent one (September).

- European Masters in Resilience
  - QA team (P5 and P1) to develop a plan for a European Masters in Reslience in collaboration with the other partners, to be submitted as deliverable 7.3 as per orignal application in November 2015
  - A separtate, parallel working group is being set up to prepare an application for EU funds to hold a European masters in resilience; the working group is being coordinated by P1 at this stage
  - All partners have shown interest in participating in the European masters application
  - Given that over the past year, P1 has been working with 7 other partners outside of RESCUR (within ENSEC) to submit an EU application for a European Masters in Social and Emotional Learning, it was agreed that if possible the two groups (RESCUR resilience and ENSEC SEL) would be joined into one masters on Resilience and Wellbeing in Education. The coordinator, who is also the coordinator of the SEL group, will ask the SEL group whether they would like to join us and inform members accordingly
  - The application for funding will be to hold a European masters awarded by the different partner universities; the modules will be prepared beforehand for the application
  - The masters will make use of both distance learning and face to face learning, such as summer schools, placements, etc
  - The coordination of the application/masters is open and will be negotiated amongst the members of the two groups (RESCUR and ENSEC SEL) once it is agreed to submit a common application
  - It may be premature to submit an application in March 2015 given that we will have to prepare the masters modules before, March 2016 may be a more realistic deadline

Next RESCUR meetings
- 2nd week of December 2014: SKYPE meeting
- 24th -26th March 2015 consortium meeting in Pavia, Italy

Carmel Cefai, coordinator
20th September 2014

APPENDICES.../

APPENDIX 1

RESCUR Teacher Training Programme
Evalutation Sheet

Section A: Your views on the organisation of the training session
Satisfaction with the organisation of the training session:

  - List 1-2 features you liked:

  - List 1-2 features you would have changed:

Content and Process of the training

  - What were the most helpful aspects of the training session?

  - What were the least helpful aspects of the training session?

  - What improvements would you suggest for the future?
.../2

Section B: Your views on the resilience curriculum

What are the main strenghts of the curriculum programme?

What are the main weaknesses of the curriculum programme?

- What are your views of the following aspects of the curriculum
  - learning goals, activities, stories, strategies:

  - Resources, pictures and material

  - Assessment checklists

What modifications if any would you recommend in the curriculum?

What issues do you forsee in the implmentation of the curriculum in the classroom and how may these be addressed?

APPENDIX 2A

RESCUR : Pilot Evaluation Tools
TEACHER ASSESSMENT OF STUDENTS’ CLASSROOM BEHAVIOR
THEME 5: BUILDING HEALTHY RELATIONSHIPS
Subtheme 1: ESTABLISHING AND MAINTAINING HEALTHY RELATIONSHIPS
Have you noticed any improvement in the pupils’ behaviour over the past 6 weeks in the following areas:
	No at all	undecided	Somewhat	Very much	Comments or examples
Making and having friends
Seeking and providing support and pro-social behavior
Nurturing relationships and school climate

Subtheme 2: DEVELOPING COOPERATION SKILLS AND EMPATHY AND ENGAGING IN RESPONSIBLE AND ETHICAL BEHAVIORS
Have you noticed any improvement in the pupils’ behaviour over the past 6 weeks in the following areas:
	No at all	Undecided,	Somewhat	Very much	Comments or examples
Sharing, cooperation and teamwork
Developing empathy
Ethical, responsible and moral behaviour

APPENDIX 2B
RESCUR : Pilot Evaluation Tools
Open question for individual interviews / focus/questionnaires : Teachers experience implementing the Pilot

How was it to implement the lessons?

What do you think about the teaching strategies (stories, games, role play) proposed in this theme?

What do you think about the engagement of the students during the lessons?

What difficulties did you found implementing the lessons?

Strengths of the theme?

Weakness of the theme?

How do you feel if the curriculum would be implemented across the full academic year? Barriers and facilitators?

Do you think other topics could be included in the theme you piloted? If so which?

What is your overall impression about your involvement in this Project?

1. What are your thoughts about your own resilience when teaching students about resilience? (Refer to the four dimensions of teacher
2. resilience)

APPENDIX 2C

RESCUR : Pilot Evaluation Tools
Students’ Focus Groups

APPENDIX 2D

RESCUR : Pilot Evaluation Tools : Teacher Self Reflection Diary
At the end of each session with the studetns, teachers would write their own reflections based on the following statement:
Looking back on today’s session, think about one aspect/incident that you think was very successful and engaging for students or unsuccessful and uninteresting for students. Describe it and reflect on why it was or was not successful and possibly what you would change about it.

APPENDIX 3

Call for Special Interest Group in Resilience in Education (SIG-R) [FROM ENSEC NEWSLETTER, SEPTEMBER 14]

“ENSEC is devoted to the development and promotion of evidence-based practice in relation to socio-emotional competence and resilience amongst school students in Europe”.

As the above excerpt from ENSEC’s mission statement illustrates, one of the objectives for the establishment of ENSEC was the development and promotion of evidence based practice in resilience in schools. Resilience is particularly concerned with positive growth and wellbeing amongst vulnerable and disadvantaged children and young people, seeking to bring about equity and social justice in our society. We are therefore calling any interested ENSCEC members who would like to join us in a special interest group in Resilience in education (SIG-R) to send us an email at carmel.cefai@um.edu.mt The objective of SIG-R will be to facilitate networking and collaboration between members including exchange of material and resources, conference presentations, placement visits, and collaborative research