**Work Packages coordination and deadlines as revised in Malta meeting (January 2013)**

1. **Work package 1 Project Management**

 Coordinator Malta (Greece critical friend)

1. **Work package 2 Development of UNIVERSAL Resilience Curriculum**

Overall Coordinator: Malta (Sweden critical friend); work distributed as follows:

* Early Years Curriculum: Greece and Croatia
* Primary (Early) School Curriculum: Malta, Sweden, Italy
* Primary ( Late) Malta, Sweden, Portugal
1. **Work package 3: Development of OPTIONAL Resilience Curriculum**

Overall Coordinator: Italy (Portugal critical friend); work to be distributed as follows:

* Resilience Curriculum for Roma students: Croatia (Portugal critical friend)
* Resilience curriculum for students from refugee, immigrant or ethnic minorities: Malta (Sweden critical friend)
* Resilience curriculum for students with disability and learning difficulties: Greece ( Portugal critical friend)
* Resilience curriculum for gifted students: Italy ( Malta critical friend)
1. **Work Package 4; Development of Parents’ Handbook ( to be developed once the curriculum framework has been agreed upon and the themes identified)**

Overall coordinator Croatia (Portugal critical friend); work to be distributed as follows:

-Early years manual Croatia (Italy critical friend)

- Primary school manual Greece (Sweden critical friend)

-Optional curriculum manual: Italy (Malta critical friend)

NB. (1) Some of the days of coordination (Italy) to go to the four sets of partners working on the optional curriculum- these partners are also to devise the parents’ activities for optional curriculum.

(2) Translation of all material by each partner to be included in WPs 2-4

**Plan and deadlines for WP 2-4**

* **Folder and subfolders on google drive: Carmel, Brigitta and Anastassios : 7 major themes and format of activities (including 3 levels of complexity) to all partners by 28th February with an example**
* **Products: to finalise framework and part of draft curriculum, putting together 6 themes and activities**
	+ **by 15th June each partner will send one theme for one age group: each one will present 7 activities for 1age group, with indications of 3 complexities in which to do the activity (initial, intermediate, advanced)**
	+ **1-3 July 2013 consortium meeting in Zagreb**
	+ **symposium in Ensec conference: presentation from each partner country on the SEL/resilience challenges and school initiatives**
1. **Work Package 5: Curriculum Piloting:**

Overall coordination of training: Greece and Malta

Overall coordination of implementation: Greece and Sweden

Work to be distributed as follows:

* ***Training of trainers***: Greece and Malta (Croatia critical friend): 1 teacher-trainer from each country; Greece to organise consortium meeting at the same time as training in Greece, with one longer meeting including both meeting and training of trainers: the trainees will be the consortium members themselves.
* Trainer needs to have expertise in both teacher trainer and in resilience/SEL, within a European perspective. The training manual used will the universal and core framework (early and primary school versions) developed by the consortium.
* **Timeline:**
* Trainer to be identified by next consortium meeting in July. Possible names: Terje Ogden

December 2013: First draft of curriculum: Universal and Optional, Early years and Primary (early and late).

Training of Trainers: February 2014

Translation: Jan-March 2014

Training of Teachers by all partners: April 2014+, staged approach, separate for early and primary teachers

Implementation: September 2014+ (all partners)

Evaluation: February 2015 (by all partners)

June 2015: modified curriculum

September 2015: external evaluation

October-December 2015: Presentation of curriculum by all partners in their respective countries at a national or regional conference

December 2015 submission of all products

NB WP 5 split in half: translation of all material to move to WP 2-4

1. **Work Package 6 Quality assurance: Sweden (Croatia critical friend)**

Production of hard and soft copies of curriculum material in all languages: all partners

1. **Work package 7 Dissemination and exploitation: Portugal (Malta critical friend)**

Presentation of curriculum in each partner country in a national/regional conference: all partners