## Dissemination Workplan
Dissemination and Exploitation Workplan - Activities - Sept.2014- Nov. 2015
|  |  | Version | 18 September 2014
Activity | Responsibility | Contributors | Target audience | Timescale
Dissemination
Presentations conferences & peer-reviewed journal papers
5th ENSEC conference – Symposium, Portugal - July 2015 | Malta CC | All partners | ENSEC participants | Jan. 2015
1.Submit abstract | Malta CC | All partners |  | March- June 2015
2 Prepare presentation | Malta CC | All partners |  | July 2015
3Prepare article submission for International Journal for child and adolescence (Pt) | Portugal | All partners |  | (ASAP)
Activity | Responsibility | Contributors | Target audience | Timescale
Any other Conferences and articles to be added in a common dissemination list that will be gathered by FMH_Portugal | All partners | All partners | National International researchers, teachers, other professionals in education | Ongoing – Oct 2015
1 Prepare dissemination file per country (An excel file built and uploaded in Google drive ( partners can then fill their file or send to FMH_Portugal) | Portugal | All partners |  | 22 September
2 Upload dissemination files also in partners área in rescur website according to partners contributions | Portugal | All partners |  | Ongoing –Oct 2015
Activity | Responsibility | Contributors | Target audience | Timescale
3 Partners to send always the evidences of the presentations or publications (power point, paper in pdf) to FMH, Portugal , so that they can be uploaded in the partners área rescur website | CC Malta |  |  | Ongoing –Oct 2015
4 CC-Malta will change website permission so that FMH, Portugalcan upload these materials in rescur website |  |  |  | ASAP
Activity | Responsibility | Contributors | Target audience | Timescale
D3 - Plan for a joint Masters degree in resilience education
1. List interested partners (within partnership and outside | Malta CC | Alll partners |  | 2015-01-01
2. Identify application (dates, criterials) | Malta CC | All partners |  | Feb. 2015
3. Prepare and submit Joint European Master Erasmus mundus application | Malta CC | All partners |  | March 2015 or Oct 2015 ( according to point 1 and 2 decisions)
Activity | Responsibility | Contributors | Target audience | Timescale
D4 Other
Poster (En) | Portugal | All partners |  | Sept 2014- Feb. 2015
Using the layout of the flyer a poster with images and the reference to the curriculum themes and sub themes will be produced. | Portugal | All partners |  | Sept 2014-March 2015
1. Send at least 3 pictures from each partner country (training, pilot, schools involved) | Portugal | Partners to send comments for improvement (one week after reception) |  | 1st Dec. 2015
2. Send first draft for partners | Portugal |  |  | End March 2015
3. Make final poster in A1 (20/25 per partner ). | Portugal |  |  | End March 2015
4. Upload version in pdf in the rescur website and other social media ( National and International) | Portugal | All partners |  | March-Nov 2015
Activity | Responsibility | Contributors | Target audience | Timescale
Brochures | Portugal | All partners |  | Jan. 2015
1 Define contents ( front page and final contents in the rescur manuals will be used to prepare this brochure). It will be made A4 size and in pdf version. Aproximately 200 will be printed. |  |  |  | March 2015
2 Prepare and send draft to partners | Portugal | Coments can be sent during the following week by all partners |  | May 2015
3 Produce Final Version | Portugal |  |  | June- Oct 2015
4 Printing/ distribution | Portugal | All partners | Distributed by each partner to local, regional & national education, organisations & agencies including key decision-makers & government departments & ENSEC participants
Flyers | All | All partners |  | Sep 2014– Nov 2015
1. Distribute flyers to key audiences (soft copies, in social networking media, face to face) | Portugal | All partners |  | Sep 2014– Nov 2015
Activity | Responsibility | Contributors | Target audience | Timescale
2. Prepare more copies of the flyers and send them to partners (400) | Portugal |  |  | October 2014
Use different social media, soft copies for the dissemination | All |  |  | Sep.-Oct. 2015
1. Check the budget for a USB ( with the logo of Rescur) It can be used to include the promotional materials of the project and given in dissemination events that the partners participate. Next meeting to decide if there is enough budget for this material. | Portugal |  |  | Sep. 2014- June 2015
If affordable produce 200 of those and distribute them in ENSEC conference 2015 | Portugal |  |  | Sep. 2014- June 2015
Activity | Responsibility | Contributors | Target audience | Timescale
Check the budget of a roll up to be used in ENSEC conference 2015 and other Seminars. The poster design can be used to produce this material. Decide to produce it accordingly with the budget next transnational meeting. | Portugal |  |  | Sept 2014 - April 2015
Web site | All | Portugal |  | Sep 2014-Oct 2015
Promote and use as much as possible the website and facebook from RESCUR Project | Portugal | Portugal |  | September 2014- Nov 2015
Use the Introduction of rescur project-videoscribe produced by CS Portugal for transnational dissemination | Portugal | All |  | October 2015
Activity | Responsibility | Contributors | Target audience | Timescale
1.Upload Portugal vídeo clip (public) En version ( with no sound) | Portugal | All |  | November 2015
2. Produce text to be recorded by partners | Portugal |  |  | December 2015
3. Each partner record the text sound and send it to P6 (Portugal) | Portugal |  |  | January
4. Prepare the video in each partner language and upload it in rescur web site (public)
Prepare a video similar to the previous in order to describe the curriculum and manual for parents ( 2 min máximum) | Portugal | All partners |  | June- Oct 2015
Exploitation
Activity | Responsability | Contributors | Target audience | Timescale
Send final products to local, regional and national education boards and key stakeholders | Each partner is responsible for identifying the list of organizations | All partners | Allow maximum exposure of the project to all interested parties throughout its life. | Sept. - Nov 2015
Send final products to European Agencies , networks of relevance (Education, SEN, …) | Malta CC | All partners | Allow maximum exposure of the project to all interested parties throughout its life. | Sept. – Nov 2015
Website must be regularly updated with news . Adding new information (papers, conferences, transnational meetings, dissemination materials such as the flyers, posters, in all partner languages, final products) | Malta CC | All partners | Allow maximum exposure of the project to all interested parties throughout its life. | Sept. 2014- Nov. 2015
If necessary partners can send the information they want to be uploaded in the website to Portugal that will do this task | Portugal | Partners are expected to send information/news about the project development at regular intervals (minimum 3 contributions). | Allow maximum exposure of the project to all interested parties throughout its life. | Sept. 2014- Nov. 2015
This can include contributions from parents, teachers, trainers as well as partners.
Activity | Responsability | Contributors | Target audience | Timescale
Adress dissemination of final products to other european countries not involved in the partnership. | Malta CC | All partners | Allow maximum exposure of the project to all interested parties throughout its life. | Sept. 2014- Oct. 2015
Partners will be expected to send information ( brochures, videos) to other networks/projects they are involved.
See viability for website maintenance after project closure | Malta CC |  | Allow maximum exposure of the project and transferability of outcomes to other interested parties. | Sept.-Oct. 2015
Check intelectual property rights of the final products produced in the partnership and produce a Consortium agreement if necessary | Malta CC | All | Allow maximum exposure of the project and transferability of outcomes to other interested parties. | Oct. 2015