## Slide 1: 18th September 4th Transnational Meeting Sweden WP 7 Dissemination and exploitation
Start Month number | 12 | End Month number | 36 | Duration in number of months | 24

## Slide 2: Topics for meeting
Application & Deliverables & Dates of deliverables in application
Dissemination strategy - Sept 2014 – Nov. 2015
Workplan/Activities - Sept 2014 – Nov. 2015

## Slide 3: Period
Start Month number | 12 | End Month number | 36 | Duration in number of months | 24

## Slide 4
Partner |  |  |  |  | 
 |  |  |  |  | Total work days
PT-Portugal |  |  |  |  | 16
MT-Malta |  |  |  |  | 14
EL-Greece |  |  |  |  | 11
IT-Italy |  |  |  |  | 11
HR-Croatia |  |  |  |  | 11
SE-Sweden |  |  |  |  | 11

## Slide 5: RESCUR APPLICATION
Dissemination and exploitation is essential for the success of the project in reaching and attracting the interest in the curriculum and its implementation at Regional, National, European and International levels.
The final products of the project will not only benefit the partner countries involved, but also will serve to enhance the promotion of educational resilience as a core competence in early and primary schools in Europe as a means to promote social inclusion, equity, growth and healthy development amongst children who may be potentially at risk in their development.
Each partner institution has its system of publicising its programmes and will use them to disseminate the final RESCUR products at regional and national levels in each country.
Dissemination and exploitation will be also through flyers, posters and presentations at relevant professional national and international meetings, uploading the curriculum on each partner’s university website, on the project website and other networks such as ENSEC, and publications in peer reviewed journals.

## Slide 6: RESCUR APPLICATION
The project plans to disseminate the availability of the final RESCUR manuals directly to the early and primary school teachers taking part in the study in each of the partner countries. It is envisaged that the twenty teachers trained in each participating country will have a multiplier effect in their own respective countries, where they will help to disseminate the curriculum in their own schools, colleges, contacts, national associations and European networks and organisations.
The soft copy of the curriculum may also be uploaded on the websites of their respective schools, associations and networks.
The participants will also be encouraged to publish their research and to create web-based social networks related to CPD in educational resilience.
The soft and hard copies of the curriculum will be also distributed in the appropriate language to the local, regional and national educational authorities of the six participating partners, including a cross section of early and primary schools in each participating country.
Copies of the final curriculum will also be sent to the regional and national educational authorities of the remaining EU countries in their own language if available, or in English if their language is different from the other languages of the project.
The curriculum will be also made available on the project website in the 7 languages of the project.
It will be also disseminated through the European Network for Social and Emotional Competence (ENSEC);
The findings of the pilot study and the process of producing the curriculum will also be published and disseminated through ENSEC’s Journal (International Journal of Emotional Education), Newsletter, website and biennial conference.
Consortium institutions and their members who are connected particularly to their regional educational systems, will be exploiting and using their connections through email, publications and conferences to promote RESCUR.
RESCUR will also be promoted at network conferences of teachers, educators, and psychologists in the education system.

## Slide 7
7.1 | Presentation of RESCUR at each partner institution |  | 
Type of outcome / product / results | Seminar |  | 
Delivery date | 30.10.2015 | Dissemination level | Public Restricted to other programme participants (including Commission services and project reviewers) Confidential, only for members of the consortium (including EACEA and Commission services and project reviewers)
Language versions | Croatian, English, Estonian, Greek, Italian, Maltese, Portuguese, Swedish
Target languages | Croatian, English, Estonian, Greek, Italian, Maltese, Portuguese, Swedish
Each partner will organise a half day continuing professional development seminar for educational authorities, policy makers and educators, promoting RESCUR as an opportunity to update themselves on European responses to the promotion of educational resilience, growth and wellbeing amongst vulnerable children, particularly in the contexts of social cohesion, inclusion and equity. This should be effective as each partner institution has contacts with the different associations and individual educators engaged in the education of vulnerable children and children coming from disadvantaged and marginalised backgrounds in their country. It will include an opportunity for the promotion and potential implementation of the curriculum in these countries. The minimum target audience for this seminar will be around 100 | 

## Slide 8
7.2 | Presentation of RESCUR at EU Conferences and publications |  | 
Type of outcome / product / results | Presentations and symposium in conferences, and peer-reviewed journal papers |  | 
Delivery date | 30.09.2012 Oct 2013 (Necessary to change this date in the application) | Dissemination level | Public Restricted to other programme participants (including Commission services and project reviewers) Confidential, only for members of the consortium (including EACEA and Commission services and project reviewers)
Use of relevant European conferences and networks of educators to promote RESCUR. ENSEC Conference in July 2013. ENSEC conference in 2015 - symposium by all the partners to present the findings of the pilot study. Each partner will also attend different relevant conferences and present papers on the relevance of the project to educators, professionals and others involved. Besides promoting the European resilience curriculum, these activities will also raise general sensitivity to the promotion of academic and social and emotional resilience for students at risk for school failure, early school leaving, and social exclusion. Finally the pilot results and the process leading to the final product will be published in a couple of papers in the European Journal of Educational Education (possibly special edition) and the European Journal of Special Needs Education. |  |  | 

## Slide 9
7.3 | Development of RESCUR into a joint masters degree
Type of outcome / product / results | Plan for a joint Masters degree in resilience education
Delivery date | 30.09.2014 30.09.2015 (Change) | Dissemination level | Public Restricted to other programme participants (including Commission services and project reviewers) Confidential, only for members of the consortium (including EACEA and Commission services and project reviewers)
Nature | Report Service / Product Demonstrator / Prototype Event Other |  | 
Language versions | English |  | 
Target languages | English |  | 
It is intended that the experience of developing a European resilience curriculum for early and primary schools, should provide sufficient knowledge and expertise to plan and develop a joint European masters in resilience education in early and primary school, preparing European teachers in this core competence. The partners in this consortium will make plans before the conclusion of the project comes to an end, to prepare a bid for the development of a masters through such programmes as the EU Lifelong Learning Programme. This might include other EU member partners not included in the present consortium. This will be discussed through skype meetings, the last transnational meeting and a preparatory meeting late in 2015 |  |  | 

## Slide 10
Dissemination Strategy - two levels:
Transnational / European level
International conferences (eg. ENSEC 2013 and ENSEC 2015 -symposium)
Publication of papers in international journals (International Journal of Emotional Education)
Brochures, flyers, videos in all partners language
Disseminate final products from wp2/3, 4 (Curriculum; Parents Manual)
Develop a joint European masters in resilience education (partners from other EU countries not included in present consortium) to train teachers in resilience education.
National level
Disseminate Project outcomes to educators in partner countries at local, regional and national levels (educational authorities, teachers) / Seminar.
Promote the introduction of the curriculum partner countries as part of the mainstream curriculum in early and primary schools.

## Slide 11: WORKPLAN – Sept. 2014 – Nov. 2015 - Dissemination & Exploitation activities
D1 - RESCUR Seminar at each partner country
D2 - Presentations and symposium in conferences and peer-reviewed journal papers
D3 - Plan a joint Masters degree in resilience education
D4 Other
  Poster (all partner languages)
  Brochures & Flyers
  Video (introduction for the rescur project) (videoscribe)
  Video (introduction for the curriculum (videoscribe)
  Website (material upload)

## Slide 12: Dissemination
Activity | Responsibility | Contributors | Target audience | Timescale
D1 - RESCUR Seminar at each partner institution |  |  |  | 
1Set date & venue 2Define list of invitations 3Organize seminar&Prepare presentations 4Prepare news to put on rescur website / 3 5 Seminar 6Upload seminar evidences on the website | Each partner is responsible for his own national seminar | All partners | Teachers, and other educational staff, Headteachers, National Education boards, Researchers, Key stakeholders | 1 January 2015 2June 2015 3July /Sept 2015 4 June/Oct 2015 5 Oct 2015 6 Two weeks after seminar
Presentations and symposium in conferences and peer-reviewed journal papers |  |  |  | 
Eg. 5th ENSEC conference – Symposium- July 2015 (submit abstract CC, Prepare presentation, Prepare article submission International Journal child Pt Update List of dissemination activities - excel file on rescur website partner area Google drive |  |  |  | 
D3 - Plan for a joint Masters degree in resilience education |  |  |  | 
Actions List interested partners (within partnership and outsider Identify application (dates, criterials) Joint European Masters Erasmus mundus? |  |  |  | 
D4 Other |  |  |  | 
Poster A1 En 20 posters (all partner languages) April meeting |  |  |  | 
Brochures 100 (manuals) Define contents Prepare Printing/distribution Roll up for ensec conference |  |  |  | 
Flyers (prepare more copies flyers) Pt 200 Greece 100 Croatia 100 Peen drive Check budget Add all materials | Pt |  | Distributed by each partner to local, regional & national education, organisations & agencies including key decision-makers & government departments & ENSEC participants | August – Nov 2015 July 2015
Web site Upload Portugal vídeo clip (public) (introduction of rescur project) (videoscribe) In rescur web site |  |  |  | 
Increase material for the public Put new from Sweden transnational meeting |  |  |  | 
Video ( the curriculum (videoscribe) Manual for parents |  |  |  | 

## Slide 13: Dissemination
Activity | Responsibility | Contributors | Target audience | Timescale
Presentations & symposium in conferences & peer-reviewed journal papers |  |  |  | 
1. 5th ENSEC conference – Symposium- July 2015 1.1submit abstract CC, 1.2 Prepare presentation 1.3Prepare article submission for International Journal for child and adolescence (Pt) 2 SEND any planned conferences and articles by individual partners 3 Prepare file to add dissemination activities by partners - excel file and upload in Google drive ( one file per country) 4. Upload dissemination activities (conferences, …) on rescur Google drive | Malta CC Malta CC Malta CC All Portugal All | All partners All partners All partners All partners All partners All partners | ENSEC participants “ National International researchers, teachers, other professionals in education | Jan 2015 March- June 2015 (ASAP) Ongoing – Oct 2015 22 September Ongoing
D3 - Plan for a joint Masters degree in resilience education |  |  |  | 
1. List interested partners (within partnership and outside 2. Identify application (dates, criterials) 3. Prepare and submit Joint European Master Erasmus mundus application | Malta CC Malta CC Malta CC | Alll partners All partners All partners |  | Jan 2015 Feb. 2015 March 2015
D4 Other |  |  |  | 
Poster (all partner languages) 1. Send 3 pictures from each partner country (training, pilot) 2. Send first draft for partners 3. Make final poster and send to each partner ( 30 ) (En) 4. Upload version in pdf in the rescur website and other social media 4.Poster translation in each partner language ? | Portugal All Portugal Portugal | All partners All partners Partners to send comments for improvement ( one week after reception) |  | 1st Nov 2015 1st Dec. 2015 Feb 2015 Feb. 2015
Brochures 1Define contents 2Prepare draft 3Final Version 4Printing/distribution | Portugal | All partners | “ | Jan 2015 March 2015 May 2015 June- Oct 2015
Flyers 1. Distribute to key audiences ( soft copies, in social networking media, face to face) 2. Prepare more copies flyers) (100 per partner) | All Portugal | All partners All partners | Distributed by each partner to local, regional & national education, organisations & agencies including key decision-makers & government departments & ENSEC participants | Sep 2014– Nov 2015 June 2015
Web site Introduction of rescur project-videoscribe 1.Upload Portugal vídeo clip (public) En version ( no sound) 2. Produce text to be taped 3. Each partner record the text sound and send to P6 4. Prepare video in each partner language and upload in rescur web site | Portugal Portugal ?? All Portugal | Portugal Portugal All All partners | “ “ “ “ | 22 September 2015 October 2015 November 2015 December 2015
Prepare video (curriculum; manual for parents) | Portugal | All partners | “ | July- Oct 2015

## Slide 14: Exploitation
Activity | Responsability | Contributors | Target audience | Timescale
Send final products to local, regional and national education boards | Each partner | All partners |  | Sept. 2015
Send final products to european agencies (Education, SEN, …) | Malta CC | All partners |  | Sept. 2015
Update Website regularly with new information (papers, conferences, transnational meetings, final products) | Malta CC | All partners Partners will be expected to submit information about the project development at regular intervals (minimum 3 contributions). This will include contributions from parents, teachers, trainers as well as partners. | Allow maximum exposure of the project to all interested parties throughout its life. | Sept. 2014- Oct. 2015
Adress dissemination of final products to other european countries | Malta CC | All partners Partners will be expected to send information ( brochures, videos to other networks/projects they are involved | Allow maximum exposure of the project to all interested parties throughout its life. | Sept. 2014- Oct. 2015
See viability for website maintenance after project closure | Malta CC |  | Allow maximum exposure of the project and transferability of outcomes to other interested parties. | Oct 2015
Prepare intelectual property rights of the final products produced in the partnership and produce a Consortium agreement | Malta CC |  | Allow maximum exposure of the project and transferability of outcomes to other interested parties. | Oct 2015

## Slide 15
INTELLECTUAL PROPERTY RIGHTS
The partnership has agreed that each partner will have full IPR on all products in their own country. Distribution and usage in other partner countries will be on a not-for-profit basis throughout the life of the project and for two years afterwards. Decisions on wider marketing and distribution will be agreed once the products’ marketability have been assessed.

## Slide 16: Action points from the meeting
Agreement, Comments, Aditions to this strategy/activities